STANDARD OPERATING PROCEDURE

IOM SOUTH SUDAN CORE PIPELINE OPERATIONS

INTERNATIONAL ORGANIZATION FOR MIGRATION (IOM)

SEPTEMBER 2026

| Document title | SOP: IOM South Sudan Core Pipeline Operations |
| --- | --- |
| Date | September 2026 |
| Version | Draft 1 |
| Status | for management comment |
| Developed by | Joey Harb, SLSC Cluster and Core Pipeline Officer, IOM South Sudan |
| Reviewed by | To be completed |
| Approved by | To be completed |
| Approval date | To be completed |
| Review cycle | Annually |

Table of Contents

Definitions and Abbreviations	2

1. Purpose and Scope	3

2. Kits and Warehouse Network	4

2.1 Standard kits and endorsement	4

2.2 Warehouse network	4

3. Roles and Responsibilities	5

3.1 Responsibilities and handovers	5

3.2 RACI matrix	6

4. Operational Workflow	6

4.1 Step 1. Procurement and prepositioning	7

4.1.1 Planning and sourcing	7

4.1.2 Thresholds and internal lead times	7

4.1.3 Procurement plan	8

4.1.4 Receipt and quality control	8

4.1.5 Prepositioning	8

4.2 Step 2. Partner onboarding	8

4.2.1 Eligibility	8

4.2.2 Onboarding	9

4.2.3 Compliance ladder	9

4.3 Step 3. Trigger and needs assessment	9

4.4 Step 4. Request and endorsement	10

4.5 Step 5. Stock release	10

4.5.1 Release procedure	10

4.5.2 Release documents	11

4.5.3 Transport to the distribution site	11

4.6 Step 6. Distribution	11

4.6.1 Changes to an agreed distribution	12

4.6.2 Loss, damage, theft and diversion	12

4.7 Step 7. Distribution reporting	12

4.8 Step 8. Post-distribution monitoring	12

4.9 Step 9. Closure	13

4.10 Cancellation and write-off	13

4.11 Documents and signatures	13

5. Information Management, Tracking and Status Analysis	14

5.1 IMS and stock status	14

5.2 Counts, rotation and expiry	14

5.3 Reporting cycle	14

5.4 CP-RTS	15

6. Pipeline Break and Buffer	15

6.1 Setting the buffer	15

6.2 Pipeline break calculation	16

6.3 Action by band	16

7. Monitoring, Risk and Safeguards	16

7.1 Risk register	16

7.2 Safeguards	17

7.3 Complaints and feedback	17

8. Annexes	17

# Definitions and Abbreviations

| Term | Definition |
| --- | --- |
| CP | Core Pipeline. The IOM managed mechanism for bulk procurement, prepositioning, warehousing and partner accessed release of SNFI and WASH emergency supplies. |
| CPR | Core Pipeline Request. The form by which a partner requests items. |
| CP-RTS | Common Pipeline Request Tracking System. The IOM online request platform. Built but not live in South Sudan. |
| DDA | Due Diligence Assessment. The partner vetting instrument for CP access. |
| ETT and DTM | Emergency Tracking Tool and Displacement Tracking Matrix, used as response triggers. |
| IMS | Information Management System. Records receipt, storage and dispatch across all CP warehouses. The single system of record for stock. |
| IN/234 | IOM Instruction on the prevention of sexual exploitation and abuse. |
| LTA | Long Term Agreement with a supplier, at unit prices fixed for the year. |
| MHM, PSEA | Menstrual Hygiene Management. Prevention of Sexual Exploitation and Abuse. |
| PDM | Post-Distribution Monitoring. |
| RRC | Relief and Rehabilitation Commission, the government body clearing humanitarian movement and distribution. |
| SLSC and SFP | Shelter, Land and Settlements Cluster. State Focal Point. |
| SWR | Stock Withdrawal Request, raised in IMS by the CP team and approved by the CP Cluster Focal Point. Its number appears on waybills and issuance forms as the WRF number. |
| WAVE | The IOM ERP system in which requisitions and purchase orders are raised and approved. |
| 5W | Who does What, Where, When and for Whom. The cluster activity reporting tool. |

Table 1: Definitions and abbreviations

# 1. Purpose and Scope

The Core Pipeline (CP) is the IOM South Sudan emergency preparedness and response mechanism for shelter, NFI and WASH supplies. IOM procures, prepositions stock in its warehouse network and releases it free of charge to eligible partners, who distribute to affected households. The CP supports over 42 organizations through five logistics hubs and two field warehouses. IOM is the Core Pipeline manager.

This SOP defines roles and responsibilities for planning, tracking, information management, reporting and status analysis across the CP team, Supply Chain, Warehouse and IT, and the handovers between IOM, the clusters and partners. SNFI and WASH follow one process and are separated only where they differ: kit contents, buffer thresholds and endorsement routing.

Modality. All CP activity is non-fee. Partners charge no fee, cost or overhead to IOM, to beneficiaries or to any third party, and IOM does not fund partner operational costs. Allocation is decided by the clusters. Partners' operational costs, including last-mile transport, are funded directly by their donors.

# 2. Kits and Warehouse Network

SUPPLIERS LTA vendors, delivered to Juba; →; JUBA main hub consolidation, dispatch, QC; →; Wau, Malakal, Bentiu, Bor logistics hubs Abyei, Renk field warehouses; →; PARTNER collects on a signed issuance form and transports to site; →; DISTRIBUTION to affected households. All locations run the same IMS instance. All quality control is completed in Juba before dispatch.. Figure 1: How supplies move through the Core Pipeline

## 2.1 Standard kits and endorsement

| Kit | Composition per household | Endorsed by |
| --- | --- | --- |
| SNFI standard kit | 2 plastic sheets 4x6m, 2 rubber rope ties, 2 blankets, 2 mosquito nets, 2 kanga, 1 kitchen set, 1 sleeping mat, 1 solar lamp, 1 NFI bag | SLSC Cluster |
| Emergency shelter kit | 2 plastic sheets 4x6m, 2 bundles of rope; 2 bundles of bamboo and 6 wooden poles where not available locally | SLSC Cluster |
| WASH standard kit | 1 bucket with tap, 1 bucket without tap, 1 filter cloth, 2 bars of soap, 290 water purification tablets, 45 PuR flocculant sachets, 1 MHM kit | WASH Cluster |
| Hygiene kit | Procured complete under the WASH LTA and received kitted | WASH Cluster |

Table 2: Standard kits and endorsing cluster

Kits are issued separately; a household may receive more than one. Kit contents are set by the clusters and are the basis of the pipeline break calculation in Section 6. Planning uses an average household size of 6 persons.

## 2.2 Warehouse network

Juba is the consolidation and dispatch point and the only quality control location. All warehouses run the same IMS instance online. All are IOM owned except one rented storage facility at Renk. The network expands with emergencies, so budgets and reporting reflect the hubs active at the time.

| Location | Type | Coverage | Access from Juba | Capacity |
| --- | --- | --- | --- | --- |
| Juba | Main hub | Consolidation, dispatch, QC, origin of all transfers |  | 6,935 sqm |
| Wau | Logistics hub | Western Bahr el Ghazal and greater Bahr el Ghazal | Road | 4,800 sqm |
| Malakal | Logistics hub | Upper Nile State | River or air | 3,600 sqm |
| Bentiu | Logistics hub | Unity State | Road | 3,120 sqm |
| Bor | Logistics hub | Jonglei State, highest volumes in 2026 | Road | 1,400 sqm |
| Abyei | Field warehouse | Returns, Sudan crisis, outbreak response | Road | 760 sqm |
| Renk | Field warehouse, rented | Renk returns and the Sudan crisis | River | To confirm |

Table 3: Warehouse network, access and storage capacity

# 3. Roles and Responsibilities

SLSC AND WASH CLUSTERS validate needs ¦ endorse targeting ¦ approve allocation ¦ avoid duplication. ↓. CORE PIPELINE MANAGER and SLSC Cluster Coordinator; HEAD OF RESOURCE MANAGEMENT. ↓; ↓. CP OFFICERS; CP MONITORING AND REPORTING; CP ASSISTANTS, CLUSTER FOCAL POINTS; SUPPLY CHAIN; WAREHOUSE. planning and forecasting, procurement plan, allocation, reporting and status analysis, closure; PDM, utilisation reporting and CP data management; approve withdrawal requests in IMS after cluster approval; request processing, partner follow up, PDM; procurement, LTAs, freight, customs, quality control, transport to hubs; receipt, storage, IMS stock input, picking and dispatch, 7 sites. SUPPORT IT: IMS and CP-RTS administration. EXTERNAL Partners distribute ¦ Logistics Cluster: supports partners' last mile, not CP prepositioning ¦ RRC: clearance for movement and distribution. Figure 2: Core Pipeline organization

## 3.1 Responsibilities and handovers

Each unit owns a defined segment of the chain. Supply Chain and Warehouse sit under the Head of Resource Management, who also holds the budget lines for transport, storage, handling and insurance. Accountability transfers at two points: when goods are received and quality cleared in Juba, and when the partner signs for release.

| Unit | Responsibilities | Hands over at |
| --- | --- | --- |
| Core Pipeline team | Demand forecast and procurement plan; specifications and bills of quantities; partner onboarding; request review and allocation with the clusters; withdrawal requests in IMS; release tracking, reporting and status analysis; PDM methodology, sampling standards and tools; utilisation reporting and consolidation of findings; CP data management. The CP Cluster Focal Point approves withdrawal requests. | Runs across the whole chain |
| Supply Chain | Market assessment, LTA management and solicitation, purchase orders in WAVE, supplier follow up, freight and customs clearance, joint quality control on receipt, transport from Juba to the field hubs. | Goods received and quality cleared in Juba |
| Warehouse | Receipt and offloading, counting, storage, IMS stock input approval, stock condition, picking, loading and dispatch at all seven locations. Handling labour through CTG; loading and offloading outsourced to the transport vendor at peak. | Signed waybill or issuance form |
| IT | IMS and CP-RTS administration, user access, automated waybills, issuance forms and the daily stock status report. |  |
| Clusters | Validate needs, endorse targeting, decide allocation, eliminate duplication. | Endorsed request to the CP team |
| Partners | Assessment, collection and last-mile distribution, insurance of items in custody, reporting and PDM. |  |
| Logistics Cluster and RRC | The Logistics Cluster supports partners' last-mile transport by road, river and air where used, not CP prepositioning. The RRC gives government clearance for movement and distribution at state and county level. | Clearance before distribution |

Table 4: Responsibilities by unit and handover points

## 3.2 RACI matrix

R does the work. A owns the outcome, one per row. C is consulted. I is informed. A in the CP team column sits with the Core Pipeline Manager unless stated.

| Activity | CP team | Supply Chain | Ware- house | Cluster | Partner |
| --- | --- | --- | --- | --- | --- |
| Demand forecast and procurement plan | R/A | C | I | C | I |
| Sourcing, LTAs and purchase orders | C | R/A | I | I |  |
| Receipt, quality control and storage | R | A | R |  |  |
| Prepositioning to the hubs | A | R | C | I |  |
| Partner onboarding and compliance | R/A |  |  | C | C |
| Post-distribution monitoring | A |  |  | I | R |
| Needs validation and request endorsement | C |  |  | A | R |
| Request review, allocation and SWR approval | R/A |  | C | C | I |
| Dispatch and release | I |  | R/A |  | C |
| Last-mile transport and distribution | C |  |  | I | R/A |
| Distribution reporting and 5W | C |  |  | C | R/A |
| Stock status analysis and reporting | R/A | C | C | I |  |
| Loss, damage and write-off | A | C | R | C | R |

Table 5: RACI matrix

# 4. Operational Workflow

Nine steps from procurement to closure. Each step opens with a reference box: trigger, who, timeline, system action, documents and next step.

1. Procurement and prepositioning; →; 2. Partner onboarding; →; 3. Trigger and needs assessment. Supply Chain with CP forecast 4 to 5 months offshore; Cluster and CP team 3 to 5 working days; Partner, DTM, Cluster 1 to 5 days. ↓. 4. Request and endorsement; →; 5. Stock release; →; 6. Distribution. Partner, CP team, Cluster 24 hours check, 5 days max; CP team, CP Cluster Focal Point, Warehouse 72 hours confirm, 3 days release; Partner 1 to 5 days after collection. ↓. 7. Reporting; →; 8. Post-distribution monitoring; →; 9. Closure. Partner 15 days target, 1 month limit; Partner; CP team on a sample 2 weeks to 4 months; CP team 30 days after PDM. Stock status in IMS: AVAILABLE > COMMITTED at Step 5 approval > RELEASED on dispatch. Target: maximum 14 days from trigger to delivery for items held in stock. Figure 3: The nine steps, owners, timelines and stock status

## 4.1 Step 1. Procurement and prepositioning

| TRIGGER Demand forecast and confirmed funding | WHO Supply Chain leads; CP team forecasts and specifies; Warehouse receives | TIMELINE 4 to 5 months offshore; customs 1 to 2 weeks |
| --- | --- | --- |
| SYSTEM ACTION Purchase order in WAVE; receipt in IMS; warehouse approves stock input | DOCUMENTS Procurement plan, bill of quantities, purchase order, pre-alert, GRV, visual control form | NEXT Step 2; prepositioning under 4.1.5 |

### 4.1.1 Planning and sourcing

- The CP team issues the demand forecast and bill of quantities, based on consumption, cluster projections and the buffer calculation in Section 6, through the procurement plan in 4.1.3.

- Supply Chain conducts a market assessment to decide local or international sourcing.

- Where a valid LTA covers the item, which is the case for almost all CP items, the order is placed against the LTA and no solicitation is needed. LTA prices are fixed for the year and quoted delivered to the Juba warehouse, freight included.

- A purchase order is raised in WAVE only once funding is confirmed and the project activated. The supplier decides the route and informs IOM of the delivery date.

Four LTAs are in force: SNFI items; WASH items, with a main and a backup vendor per item; inland transport; and customs clearing and forwarding. Offshore lead time is 4 to 5 months. Customs clearance takes 1 to 2 weeks and is charged once per consignment.

### 4.1.2 Thresholds and internal lead times

| Value in USD | Approval | Solicitation | Internal lead time |
| --- | --- | --- | --- |
| 0 to 4,999 | Supply Chain Officer | 1 quotation | 7 days |
| 5,000 to 20,000 | Head of Supply Chain | 3 quotations | 14 days |
| 20,001 to 100,000 | Chief of Mission | 3 quotations | 14 days |
| 100,001 to 199,999 | Chief of Mission | 3 quotations and a UNGM tender | 21 days |
| 200,000 to 299,999 | Chief of Mission | 3 quotations, UNGM tender, Manila review | 28 days |
| 300,000 and above | Chief of Mission | 3 quotations, UNGM tender, Manila review, Bid Evaluation Committee | 42 days |

Table 6: Approval, solicitation and internal lead time by value

Internal lead time runs inside WAVE and is added to the offshore lead time when planning replenishment. A Bid and Award Summary with an Evaluation Report is required from USD 5,000. Requests above USD 200,000 need a Procurement Process Review code from the Manila Supply Chain Unit before award. For items under LTA only requisition, approval and purchase order apply.

### 4.1.3 Procurement plan

The procurement plan is the formal handoff from the CP team to Supply Chain; Supply Chain does not act without it. The CP team completes the CP SNFI and CP WASH tabs of the IOM South Sudan Procurement Plan workbook at the start of the project year and updates them when the buffer review changes the forecast. Each line states: item, type, category, priority, likelihood of purchase, estimated cost, quantity, delivery location, valid LTA, submission date, procurement method, days required, projected and actual purchase order date, status and remarks. Supply Chain tracks progress in the procurement tracker.

### 4.1.4 Receipt and quality control

All items are received and quality controlled in Juba before dispatch to the field. CP consignments use the inspection receipt type, set at purchase order stage.

| Check | Requirement |
| --- | --- |
| Pre-alert | Supply Chain or the CP team sends the pre-alert with the purchase order so the warehouse plans space. Receipts and withdrawals are scheduled so they do not coincide. |
| Visual control | Boxes opened on the truck to confirm the correct items. Joint check by warehouse, CP and procurement of quantity, packaging, marking, weight, condition and transport damage. Supplier Certificate of Conformity and Quality Certificate collected. Visual control form completed before acceptance. |
| Counting | Two independent counts, warehouse and CP, reconciled before the receipt is signed, with the driver present. |
| Non-conformance | Photographs before signing. Damage recorded and agreed by warehouse, CP and procurement. Unacceptable items returned to the vendor at no cost to IOM; minor deficiencies attract a penalty per item. Excess quantities refused or recorded on the overage report. |
| Recording | Stock registers in IMS at purchase order stage and becomes available when the warehouse approves the stock input. |

Table 7: Receipt and quality control checks

### 4.1.5 Prepositioning

Stock is prepositioned to the field hubs within a 6 to 8 month window against cluster projections, so minimum stock is in place before access closes. Supply Chain decides the transport mode with the CP team on budget and access (Table 3). Road transport is priced per truck by destination and truck size under the transport LTA, checkpoint costs included; destinations off the schedule are quoted case by case. Loading and offloading contracted to the transport vendor at peak costs about USD 200 per truck.

## 4.2 Step 2. Partner onboarding

| TRIGGER Organization applies, or the cluster proposes it | WHO Partner, Cluster Coordinator, CP team | TIMELINE 3 to 5 working days from a complete file |
| --- | --- | --- |
| SYSTEM ACTION Partner record created; Requester account once CP-RTS is live | DOCUMENTS DDA form, CP distribution agreement 2026, guidance checklist, authorization form | NEXT Step 3 |

### 4.2.1 Eligibility

All six conditions apply. The cluster confirms them at onboarding and annually.

| Condition | Evidence |
| --- | --- |
| Legally registered | Current registration documents in the partner file |
| Active cluster member | Attends coordination meetings and reports through the 5W |
| Presence and access | Distributes directly in the target area, without an intermediary |
| Humanitarian purpose | Response or preparedness intervention consistent with the response plan |
| Reporting up to date | No distribution report overdue for the same state |
| Own operational funding | Funds transport from the warehouse and insurance of items in custody, with last-mile transport built into its own proposals |

Table 8: Partner eligibility

### 4.2.2 Onboarding

- The organization submits the DDA form and registration documents to the cluster. The DDA is mandatory and re-validated every 24 months.

- The cluster validates capacity, presence and coordination compliance within 3 to 5 working days.

- The CP team issues the distribution agreement on the IOM Legal template, with the guidance checklist and, where applicable, the authorization form.

- The CP team registers one partner focal point as Requester, responsible for requests, reporting and liaison with IOM.

- The CP team delivers orientation on this SOP, reporting, data protection, PSEA, GBV risk mitigation and the non-fee model. Refresher training runs twice a year and when a form or system changes.

The agreement does not guarantee release: each release depends on cluster endorsement of the request and on stock availability.

### 4.2.3 Compliance ladder

| Stage | Trigger | Consequence |
| --- | --- | --- |
| Reminder | Report or PDM overdue, or a data quality issue | Written reminder with a deadline, copied to the cluster |
| Hold | Report still overdue, or repeated request errors | New requests for that state not processed until received |
| Suspension | Persistent non-reporting, unreported loss, diversion, charging beneficiaries, or any breach | All CP access suspended pending investigation, decided by the Core Pipeline Manager with the cluster coordinator and notified in writing |
| De-registration | Substantiated fraud, diversion, PSEA violation, or refusal to co-operate with an investigation | Agreement terminated and referred to mission management |

Table 9: Compliance ladder

Reinstatement requires the outstanding obligation to be met, a corrective action plan agreed with the CP team and the cluster, and written confirmation by the Core Pipeline Manager.

## 4.3 Step 3. Trigger and needs assessment

| TRIGGER ETT or DTM report, cluster alert, SITREP, government notification | WHO Partner assesses; cluster validates; CP team checks stock | TIMELINE Assessment within 1 to 5 days; valid for 3 months |
| --- | --- | --- |
| SYSTEM ACTION None. Assessment attached to the request at Step 4 | DOCUMENTS Needs or rapid assessment tool, assessment and verification report, vulnerability index | NEXT Step 4 |

Needs are validated through the cluster and cross-checked against IOM assessments and the 5W. Where stock is less than need, the cluster and the CP team apply the criteria below together. Within a location, beneficiaries are prioritised with the cluster vulnerability index, and the partner reports the criteria applied.

| Need and urgency | Feasibility and fairness |
| --- | --- |
| Severity and scale of need and living conditions Recency of displacement or alert Protection risks and highly vulnerable groups Time since last assistance; unassisted locations | Access and safe delivery within the season Do no harm and social cohesion Where limited stock has most effect Complementarity with other sectors; partner capacity |

Table 10: Prioritisation criteria where stock is less than need

## 4.4 Step 4. Request and endorsement

| TRIGGER Validated assessment and confirmed partner capacity | WHO Partner submits; CP team reviews; SFP and cluster endorse | TIMELINE 24 hours completeness check; 5 days maximum to endorsement |
| --- | --- | --- |
| SYSTEM ACTION Request registered with a unique reference; stock checked in IMS | DOCUMENTS SNFI Pipeline Request Form or CPR Form 2026, assessment and verification report | NEXT Step 5 |

The partner uses the current form version for each request. Until CP-RTS is live, the form is sent in Excel by email to the cluster pipeline mailbox, CP team in copy, and the request reference is quoted in all later correspondence. Mandatory content: date, organization and contacts, project, need and planned intervention, duration, target households, location, planned response date, confirmation of no overdue report for the state, and per line the item code, quantity, warehouse code and transport arrangement.

- Completeness review, 24 hours. The CP team checks item codes, warehouse, quantities against caseload and kit, assessment validity and overdue reports; about 10 per cent of requests carry a wrong item or warehouse. Incomplete requests are returned with the correction needed. A partner already funded to procure the same items discloses it here, and allocation takes it into account.

- Sub-national review, 48 hours. The SFP reviews and may request more information. Without feedback in 48 hours the review passes to national level.

- National approval, 24 hours. The cluster approves and forwards to the CP team. Multi-sector requests are facilitated by the SLSC Cluster with the clusters concerned.

- Allocation. The CP team confirms stock and makes the final allocation; the partner confirms readiness.

Rejected requests are returned with reasons. A change of location or caseload after endorsement is justified in writing to the cluster, CP team in copy, within 24 hours and before activities start.

## 4.5 Step 5. Stock release

| TRIGGER Endorsed request received by the CP team | WHO CP team raises; CP Cluster Focal Point approves; Warehouse dispatches; partner collects | TIMELINE Availability confirmed in 72 hours; release in 3 working days; held 15 days maximum |
| --- | --- | --- |
| SYSTEM ACTION SWR raised and approved in IMS; stock committed, then released on dispatch | DOCUMENTS Approved SWR, issuance form or waybill, packing list | NEXT Step 6 |

The only authority to dispatch is an SWR approved in IMS by the CP Cluster Focal Point. No email, verbal instruction or other form replaces it, for releases to partners and for transfers between hubs.

### 4.5.1 Release procedure

- The CP team confirms availability to the partner within 72 hours and raises the SWR in IMS.

- The CP Cluster Focal Point approves the SWR; the stock moves from available to committed.

- The warehouse checks stock and condition, plans the loading and picks according to the rotation rules in Section 5.2. There is no minimum volume and requests are not held for consolidation.

- The partner confirms the collection date and time at least 24 hours in advance; without notice the warehouse may refuse release.

- Approved stock is held for 15 days. Uncollected lines are then returned to available stock under Section 4.10 and can be released to other partners. The partner and cluster are notified.

- At collection the partner checks quantity and condition and signs; responsibility transfers at signature. The warehouse records the release in IMS.

### 4.5.2 Release documents

|  | Waybill | Issuance form |
| --- | --- | --- |
| Used for | Transfers between IOM locations | Release to a partner |
| Issued per | Truck loaded; one SWR on ten trucks gives ten waybills | Release, referencing the CPR |
| Copies | Five: white to IOM with the invoice, pink consignor, yellow requesting unit, green recipient, blue book | Signed copy kept by the warehouse and by the partner |
| Signed by | Driver at pickup, receiver on delivery | Releasing warehouse staff and partner collector, stamped and dated |
| Liability | Carries transport terms and driver liability for losses | None; responsibility passes to the partner on signature |

Table 11: Waybill and issuance form

Both documents are generated from IMS and carry the SWR number, which links request, dispatch and receipt. Signed copies return to the warehouse within 3 working days of pickup.

### 4.5.3 Transport to the distribution site

IOM transports stock to the hubs as part of prepositioning. Partners hold full responsibility for last-mile transport from the warehouse to the distribution site, funded by their donors, and coordinate with the Logistics Cluster where common services are used.

## 4.6 Step 6. Distribution

| TRIGGER Items collected by the partner | WHO Partner, fully responsible after handover | TIMELINE Within 1 to 5 days of collection |
| --- | --- | --- |
| SYSTEM ACTION None until reporting; stock already released in IMS | DOCUMENTS Distribution plan, registration and signed distribution list, consent forms | NEXT Step 7 |

| Requirement | Standard |
| --- | --- |
| Community information | Targeting criteria, kit contents, timeline, complaint channels and free aid policy communicated in advance through leaders and authorities, including date, place and what to bring. Specific outreach to older persons, persons with disabilities, and women and child headed households. |
| Registration | Standard tools; duplicate checks across partners, then cluster validation. IOM has no presence at distributions. After handover its role is PDM on the items, and issues found are raised with the partner and the cluster. |
| Team and site | Mixed gender team trained in PSEA and GBV risk mitigation, with a named team leader. Neutral, secure, accessible site agreed with authorities and the community, with separate entry, registration, distribution and exit points, shaded waiting area, water, first aid and crowd control. Door to door delivery for those who cannot reach the site. |
| Complaints desk | Staffed at every site by trained personnel; hotline and referral pathways communicated before and during distribution. |
| Verification | Identity verified on site; distribution list attested by community leaders or site management. Discrepancies, duplicates and attempted fraud reported to the CP team and the cluster the same day. |
| Visibility | Branding and banners as specified for the intervention and communicated before release. Evidenced with photographs; images of people require signed consent. |

Table 12: Distribution standards

To be confirmed: the IOM South Sudan complaints hotline number.

### 4.6.1 Changes to an agreed distribution

Changes to timing, site or caseload may be made for security, change in need, logistics or on the advice of local authorities. They are justified in writing with supporting documents, agreed with the cluster before implementation, with the CP team informed, and reported in the distribution report.

### 4.6.2 Loss, damage, theft and diversion

The partner reports any incident to the CP team and the cluster within 24 hours of becoming aware, on the Loss and Damage form, with a police or authority report where applicable. IOM investigates each case and informs IOM staff security as required. Late or missing reports trigger the compliance ladder. The partner insures items from collection until distribution; IOM does not insure CP items after release.

Loss, damage, theft or diversion; →; Partner aware 24 hour clock starts; →; Partner reports to CP team and cluster; →; CP team investigates, reports to IOM security. ↓; ↓; ↓. Loss and Damage form; Police or authority report where applicable; Corrective action and compliance ladder. Figure 4: Incident reporting, 24 hours

## 4.7 Step 7. Distribution reporting

| TRIGGER Distribution completed | WHO Partner reports; CP team tracks; cluster monitors | TIMELINE 15 days target; one month maximum; 5W by month end |
| --- | --- | --- |
| SYSTEM ACTION Report logged against the request reference | DOCUMENTS SNFI distribution report or WASH distribution and utilisation report, signed beneficiary list, photographs | NEXT Step 8 |

The report covers the signed beneficiary list, items by location, results and difficulties, any loss or damage, photographs with consent, and any training on item use with attendance by sex, age and disability. The partner updates the 5W, CP team in copy. A partner holding stock at a prepositioning site reports movements there as they occur and states received, distributed and balance. The CP team tracks reports and flags overdue ones to the cluster monthly.

## 4.8 Step 8. Post-distribution monitoring

| TRIGGER Distribution report submitted | WHO Partner for partner PDM; CP team for CP PDM on a sample of distributions | TIMELINE 2 weeks to 4 months after distribution |
| --- | --- | --- |
| SYSTEM ACTION PDM report logged against the request reference | DOCUMENTS PDM questionnaire and narrative template for the stream | NEXT Step 9 |

Two separate PDMs are carried out.

Partner PDM. Partners carry out PDM of the overall distribution process, as required by the cluster and by their own donors.

CP PDM. The CP team carries out PDM on a sample of distributions, focused on the items, as a pipeline donor requirement. It is done by CP assistants with occasional PSU support and is budgeted per project.

PDM assesses satisfaction, item quality and use, and protection concerns, and feeds item specifications, replenishment and prioritisation. The standard sample is 95 per cent confidence with a 10 per cent margin of error.

Recommendation. Standardise the PDM tools used by the different partners.

4.9 Step 9. Closure

| TRIGGER PDM report received or waiver approved | WHO CP team closes; Warehouse reconciles; CP monitoring and reporting validates PDM | TIMELINE Within 30 days of PDM receipt |
| --- | --- | --- |
| SYSTEM ACTION Request reference closed; stock reconciled in IMS | DOCUMENTS Closure record and reconciliation | NEXT Feeds Sections 5 and 6 |

| Closure condition | Evidence in the request file |
| --- | --- |
| Distribution reported | Distribution report validated and 5W updated |
| Monitoring completed | PDM report received, or waiver approved |
| Stock reconciled | No unexplained variance in IMS between released and reported quantities |
| Incidents closed | Any loss and damage case investigated and closed |
| File complete | Request, assessment, endorsement, SWR, release documents, beneficiary list, reports |

Table 13: Closure conditions

## 4.10 Cancellation and write-off

There is no partner returns process. Lines a partner does not collect within 15 days are cancelled from the SWR by the CP team and return from committed to available in IMS without physical movement. If the partner has another endorsed response for the same items, a new SWR is raised against it. To limit cancellations, the CP team requests exactly the items and quantities the partner needs rather than full standard kits.

Items released but not distributed remain the partner's responsibility and cannot be retained, repurposed or moved without written agreement. The CP team and the cluster decide their redirection; any physical return is an exception, notified to the warehouse in advance and checked on arrival.

Damaged, deteriorated or expired items are recorded as impaired, segregated and written off or disposed of under the IOM Warehouse Manual. To be confirmed: write-off authority and value threshold.

## 4.11 Documents and signatures

| Document | Step | Signed by | Held in |
| --- | --- | --- | --- |
| Procurement plan and bill of quantities | 4.1 | CP Officer | CP file, procurement tracker |
| Purchase order | 4.1 | Per IOM delegation of authority | WAVE system |
| GRV and visual control form | 4.1 | Warehouse, CP and procurement | Stock receipt file |
| DDA form and distribution agreement | 4.2 | Partner, and IOM for the agreement | Partner file |
| Assessment and verification report | 4.3 | Partner and cluster | Request file |
| Request form and cluster endorsement | 4.4 | Partner focal point; Cluster Coordinator | Request file |
| Stock Withdrawal Request | 4.5 | CP Cluster Focal Point | IMS |
| Waybill or issuance form | 4.5 | See Section 4.5.2 | Warehouse file and IMS |
| Beneficiary list and consent forms | 4.6 | Beneficiaries and partner | Request file |
| Loss and damage report | 4.6 | Partner and CP team | Incident file |
| Distribution report, 5W, PDM report | 4.7, 4.8 | Partner or author | Request file; cluster database |
| Closure record | 4.9 | CP Officer | Request file |

Table 14: Documents that carry a signature or audit trail

# 5. Information Management, Tracking and Status Analysis

Purchase order receipt; →; IMS single system of record; →; Daily stock status report. Quality control in Juba; →; →; Weekly approved against released check. Donation in kind; →; →; Partner stock list, 15th and 30th. Hub transfer; →; →; Monthly status snapshot. AVAILABLE > COMMITTED > RELEASED IMPAIRED stock is segregated. Figure 5: IMS inputs and outputs

## 5.1 IMS and stock status

IMS is the single system of record for CP stock from receipt to dispatch, updated in real time at all locations. Where records disagree, IMS prevails. PALMS is no longer used; stock and bin cards are a secondary warehouse control only. Stock input is categorised at entry as new delivery, donation in kind, hub transfer, returned items or items on loan, and becomes available once the warehouse approves it.

| Status | Meaning | Trigger | Set by |
| --- | --- | --- | --- |
| Available | In stock, quality cleared, not committed | Stock input approved | Warehouse |
| Committed | Held against an approved, uncollected SWR; not shown as available | SWR approved | CP Cluster Focal Point, automatic |
| Released | Dispatched on a signed waybill or issuance form | Dispatch and signature | Warehouse |
| Impaired | Damaged, deteriorated or expired; segregated pending write-off | Inspection finding | Warehouse, CP confirms |

Table 15: Stock status in IMS

The CP team reconciles approved SWRs against recorded releases weekly. The buffer and earmarked split will be held in the new CP database; until then it is kept manually.

## 5.2 Counts, rotation and expiry

| Control | Rule |
| --- | --- |
| Spot checks | Daily, weekly and monthly on selected lines, reconciled with IMS |
| Physical count | June and December at all locations, as required by IOM for every mission warehouse; report shared with the Supply Chain Division. Full count also at every change of warehouse manager |
| Rotation | FIFO by date of entry in IMS and stock card. Exceptions, recorded: LIFO where newer stock expires sooner; priority release of stock charged to a project code nearing its end date |
| Expiry | The warehouse issues a standing expiry alert to the CP team, which plans distribution or reallocation. Any expiry is reported in the monthly snapshot with the date of the first alert |
| Discrepancies | Investigated, documented and adjusted in IMS with warehouse and CP sign off; repeated cases escalated to the Core Pipeline Manager and Supply Chain |

Table 16: Counts, rotation and expiry

## 5.3 Reporting cycle

| Product | Frequency | Produced by | Audience |
| --- | --- | --- | --- |
| IMS stock status report | Daily, automatic | IMS | CP team, Warehouse, Supply Chain |
| Approved against released check | Weekly | CP team | Core Pipeline Manager |
| Partner stock list | 15th and 30th | CP team | All CP partners |
| Core Pipeline status snapshot | Monthly | CP team | Clusters, donors, partners, management |
| Reporting compliance tracker | Monthly | CP team | Clusters, CP management |
| Consumption and buffer review | Quarterly | CP team | CP management, clusters |

Table 17: Reporting cycle

The monthly snapshot is the main status analysis product: stock by hub, stock en route, prepositioning plan, funding, consumption trend, pipeline break projection and the buffer band for each stream, stated explicitly.

## 5.4 CP-RTS

CP-RTS is in use in other missions but not live in South Sudan. Until it is, the offline process in Section 4.4 applies. When live, its roles map to existing posts:

| System role | Held by | Function |
| --- | --- | --- |
| Requester | One focal point per partner | Submits requests and reports, sees available stock |
| Approver | Cluster and CP team | Endorses and approves requests |
| Stock Manager | Warehouse | Stock input, transfers, release status |
| Administrator | CP team and IT | Users, warehouses, item catalogue, settings |

Table 18: CP-RTS roles

For review: CP-RTS is not connected to procurement, and its link to IMS is not defined. The IMS daily stock status report exists, but how it would feed availability in CP-RTS is not confirmed. Points to settle before go-live: showing partners available stock net of committed stock; keeping the SWR approval in IMS as the single release authority; migrating existing request references; retraining partner focal points and closing the offline route on a set date.

# 6. Pipeline Break and Buffer

The earlier buffer figures were set by the clusters: 30 per cent for SNFI, about four months of an annual supply of 130,000 kits, and 40,000 kits for WASH, a third of the annual target of 1.2 million people. Both aimed at about four months of supply but did not change with consumption. This SOP keeps the aim and states the calculation explicitly, as used in the monthly status snapshot.

Buffer = average monthly consumption x procurement lead time (4 months). Status band; SNFI standard kits; WASH standard kits; Action. HEALTHY above twice the buffer; above 88,000; above 136,000; Normal operations, prepositioning continues. CONSUMING BUFFER one to two times the buffer; 44,000 to 88,000; 68,000 to 136,000; Start replenishment, notify clusters and donors. URGENT REPLENISHMENT below the buffer; below 44,000; below 68,000; Escalate, ration allocations. SNFI 11,000 kits a month x 4 = 44,000. WASH 17,000 kits a month x 4 = 68,000.. Figure 6: Buffer formula and status bands

## 6.1 Setting the buffer

The four month factor is the average time for regionally procured items to reach South Sudan, so the buffer covers consumption while a replenishment order is in transit. It is calculated per stream, refreshed quarterly against actual consumption, and the lead time factor is reviewed annually against procurement performance. Changes are recorded in the monthly snapshot. The buffer is a planning and advocacy figure at cluster level, not a donor reporting category; donor reporting tracks kits against the project that funded them.

## 6.2 Pipeline break calculation

The break date is the date on which any item of a kit runs out: one missing item breaks the kit. Each kit in Section 2.1 is assessed on its own item list; hygiene kits and the MHM kit in the WASH kit count as single items. Locally sourced bamboo and wooden poles are excluded. Stock is counted in country, en route and under procurement, reported separately.

Sourcing gaps: the solar lamp in the SNFI kit has no active LTA and breaks that kit until it is re-sourced, substituted or removed. Bamboo for the emergency shelter kit has no LTA or price.

## 6.3 Action by band

| Band | Action by the CP team |
| --- | --- |
| Healthy | Prepositioning continues against cluster projections. Buffer calculation confirmed quarterly. |
| Consuming buffer | Replenishment starts at once: update consumption, issue the bill of quantities, confirm funding, raise the purchase order on activation. With a 4 to 5 month lead time, an order raised at the buffer floor arrives after stock-out. |
| Urgent replenishment | Written escalation to CP management, clusters and donors. Allocations rationed against the criteria in Section 4.3. Emergency procurement and regional stock borrowing examined. |

Table 19: Action by status band

# 7. Monitoring, Risk and Safeguards

Receipt; Storage; Release; Distribution; After. Joint QC, two counts, vendor penalties; Spot checks, June and December count; Approved SWR only, weekly reconciliation; Partner responsible, 24 hour incident reporting; Report, 5W, PDM, closure. Figure 7: Control points across the chain

The CP is donor funded and subject to audit. Partners keep records of each distribution, including beneficiary data, locations and photographs taken with consent, and make them available on request. Utilisation reporting is mandatory.

## 7.1 Risk register

| Risk | Level | Control |
| --- | --- | --- |
| Pipeline break and stock-out | High | Buffer bands and triggers (Section 6); quarterly consumption review; early escalation to donors |
| Stock held and not collected | High | 15-day holding limit; committed status; weekly reconciliation |
| Partner non-reporting | High | Reporting tracker; hold on new requests; compliance ladder |
| PSEA and protection incidents | High | Trained distribution staff; complaints desk at every site; referral pathways |
| Access and seasonal isolation | High | Dry season prepositioning; hub network |
| Loss or diversion after release | Medium | Partner insurance; 24 hour incident reporting; release documents; PDM |
| Expired or stranded stock | Medium | Expiry alert acted on by the CP team; rotation exceptions (Section 5.2) |
| Poor quality items | Medium | Joint QC in Juba; supplier certificates; vendor penalties; PDM feedback |
| Duplication or data breach | Medium | Cluster endorsement and 5W cross-check; unique request references; data protection rules |

Table 20: Risk register

## 7.2 Safeguards

| Instrument | Obligation |
| --- | --- |
| PSEA, IN/234 | Binding on IOM and partner staff at every step involving beneficiaries. Allegations are reported immediately through IOM PSEA channels. |
| Protection and GBV | IOM and CARE distribution guidance applied to site, timing, team and queue arrangements (Section 4.6). |
| Data protection | IOM Data Protection Policy and Principles apply to all beneficiary data; the partner signs the data protection annex. Signed consent before any image of a beneficiary is used. |
| Anti-fraud | Non-fee model enforced and distribution free without exception; incidents reported within 24 hours. |
| Quality | Cluster technical specifications and SNFI Cluster QA and QC procedures at receipt; condition checked by the partner at collection. |

Table 21: Safeguards

## 7.3 Complaints and feedback

Feedback is recorded, acted on and closed. Issues raised during a distribution are resolved on the day.

1. DEFINE; →; 2. COLLECT AND SORT; →; 3. ACT; →; 4. ANALYSE. Channels agreed with the community; Recorded, categorised and routed; Corrective action and response to the person; Patterns reported in distribution report and PDM. PSEA and protection allegations bypass this loop and go directly to IOM PSEA and protection channels.. Figure 8: Complaints and feedback loop

# 8. Annexes

The CP team keeps one current version of each annex; partners use the latest issued version. Items highlighted are still to be produced or updated.

| Group | Documents | Used at |
| --- | --- | --- |
| A. Partner agreement | CP Distribution Agreement 2026 with guidance checklist, authorization form, DDA form, IOM Data Protection Policy and Principles, PSEA policy IN/234. The agreement and data protection annex are signed by the partner. | 4.2 |
| B. Assessment | Needs and rapid assessment tool, assessment and verification report format, South Sudan vulnerability index | 4.3 |
| C. Requests | SNFI Pipeline Request Form, CPR Form 2026, offline stock request form, item code list, item catalogue (WASH 2022 on file, to update; no SNFI catalogue) | 4.4 |
| D. Release | IMS generated waybill and issuance form, current samples to attach | 4.5 |
| E. Distribution and reporting | Distribution list template (2013 version on file, to update), audio-visual consent form, loss and damage form, SNFI distribution reporting format, WASH distribution and utilisation report, PDM questionnaires and narrative templates | 4.6 to 4.8 |
| F. Warehouse | Stock card and receiving report forms | 5.2 |
| G. Safeguards | GBV risk mitigation distribution guidance, SNFI Cluster QA and QC procedures, feedback mechanism guidance | 4.1, 4.6, 7 |
| H. Reference | Procurement SOP, procurement plan workbook, procurement tracker, SNFI and WASH LTA price lists, transport LTA, supply chain workflow, WASH Cluster CP SOP, Warehouse SOP (version 0.5, to update to IMS) | 3, 4.1, 5 |
| I. Tools to produce | Contact list; partner quick guide; CP budget breakdown tool | All |

Table 22: Annexes